## Bugs
Project | Issue Type | Bug ID | Summary | Priority | Severity | Status | Components | Affects Version | Fix Version | Environment | Module | Feature | Test Case ID | Reproducibility | Reporter | Assignee | Labels | Linked Requirement | Description | Created
Manual QA Case Study - Clinic | Bug | BUG-CLN-001 | Fee policy message incorrect when cancelling within 30 minutes | High | Major | Open | Appointments | 1.0.0 |  | Staging · Chrome 120 · Windows 10 | Appointments | Cancel | CLN-050 | Always | Tanzid | Unassigned | portfolio, clinic, policy | REQ-CLN-CANCEL | Steps: 1) Create appointment T+30m 2) Attempt cancel Expected: Policy warns of partial fee per spec Actual: Shows full fee or ambiguous text | 2025-10-03
Manual QA Case Study - Clinic | Bug | BUG-CLN-002 | Double booking allowed for overlapping slots (15 min overlap) | Critical | Critical | Open | Appointments | 1.0.0 |  | Staging · Firefox 118 · Ubuntu 22.04 | Appointments | Create | CLN-031 | Sometimes | Tanzid | Unassigned | portfolio, clinic, blocking | REQ-CLN-CONFLICT | Steps: 1) Book 10:00–10:30 2) Attempt to book 10:15–10:45 with same doctor Expected: Conflict error and block Actual: Booking confirmed (overlap allowed) | 2025-10-03
Manual QA Case Study - Clinic | Bug | BUG-CLN-003 | OTP resend not throttled (can spam requests) | High | Major | Open | Auth | 1.0.0 |  | Staging · Android Chrome 126 | Auth | Registration & OTP | CLN-002 | Always | Tanzid | Unassigned | portfolio, clinic, security | REQ-CLN-REG-OTP | Steps: 1) Start signup 2) Tap 'Resend OTP' rapidly 10x Expected: Cooldown and clear message Actual: Multiple OTPs sent; no rate-limit | 2025-10-03
Manual QA Case Study - Clinic | Bug | BUG-CLN-004 | Doctor filter 'Cardio + rating ≥4' returns unrelated specialties | Medium | Minor | Open | Discovery | 1.0.0 |  | Staging · Chrome 120 · macOS 13 | Discovery | Search/Filter | CLN-020 | Intermittent | Tanzid | Unassigned | portfolio, clinic, ui | REQ-CLN-SRCH | Steps: 1) Search Cardio 2) Apply rating ≥4 Expected: Only cardiology specialists with rating ≥4 Actual: Mixed specialties appear | 2025-10-03
Manual QA Case Study - Clinic | Bug | BUG-CLN-005 | Profile save success toast overlaps header on small screens | Low | Trivial | Open | Profile | 1.0.0 |  | Staging · iPhone 14 Safari | Profile | Patient Profile | CLN-010 | Always | Tanzid | Unassigned | portfolio, clinic, ui | REQ-CLN-PROFILE | Steps: 1) Edit profile 2) Save Expected: Toast visible without blocking navigation Actual: Toast overlays header causing back button tap miss | 2025-10-03
Manual QA Case Study - Clinic | Bug | BUG-CLN-006 | Report PDF downloads without auth after session timeout | Critical | Blocker | Open | Records | 1.0.0 |  | Staging · Edge 120 · Windows 11 | Records | Reports Access | CLN-070 | Always | Tanzid | Unassigned | portfolio, clinic, security, blocking | REQ-CLN-RECORDS | Steps: 1) Login and open report detail 2) Wait for session to expire 3) Click download link Expected: Redirect to login Actual: PDF downloads directly | 2025-10-03
Manual QA Case Study - Clinic | Bug | BUG-CLN-007 | Reschedule flow loses previous appointment state (ghost booking) | High | Major | Open | Appointments | 1.0.0 |  | Staging · Chrome 120 · Windows 10 | Appointments | Reschedule | CLN-040 | Sometimes | Tanzid | Unassigned | portfolio, clinic | REQ-CLN-RESCH | Steps: 1) Reschedule 10:00→11:00 2) Refresh page Expected: Only new slot remains Actual: Both old and new appear in list intermittently | 2025-10-03
Manual QA Case Study - Clinic | Bug | BUG-CLN-008 | Timezone display off by +1h for reminders | Medium | Major | Open | Notifications | 1.0.0 |  | Staging · Android Chrome 126 | Notifications | Email/SMS | CLN-060 | Sometimes | Tanzid | Unassigned | portfolio, clinic, tz | REQ-CLN-NOTIF | Expected reminders to reflect Asia/Dhaka (UTC+6). Actual SMS shows +1h mismatch. | 2025-10-03
Manual QA Case Study - Clinic | Bug | BUG-CLN-009 | Search result pagination resets filters on page 2 | Low | Minor | Open | Discovery | 1.0.0 |  | Staging · Firefox 118 · Ubuntu 22.04 | Discovery | Search/Filter | CLN-020 | Always | Tanzid | Unassigned | portfolio, clinic, ui | REQ-CLN-SRCH | Steps: 1) Apply filters 2) Go to page 2 Expected: Filters persist Actual: Filters cleared | 2025-10-03
Manual QA Case Study - Clinic | Bug | BUG-CLN-010 | Invalid phone format accepted during registration | High | Major | Open | Auth | 1.0.0 |  | Staging · Chrome 120 · Windows 10 | Auth | Registration & OTP | CLN-001 | Always | Tanzid | Unassigned | portfolio, clinic, validation | REQ-CLN-REG-OTP | E.164 not enforced; accepts 12345 leading to SMS failure. | 2025-10-03

## HowToUse
Field | Guidance
Summary | One-line problem statement
Priority | P1=Highest, P4=Low (use High/Medium/Low here)
Severity | Blocker/Critical/Major/Minor/Trivial
Components | Functional area of the app
Affects Version | Version under test (e.g., 1.0.0)
Environment | OS/Browser/Device
Module | Module name matching test assets
Feature | Feature name matching test assets
Test Case ID | Cross-reference to TEST_CASES.csv
Reproducibility | Always/Sometimes/Rarely
Labels | Comma-separated keywords
Linked Requirement | Map to RTM requirement ID
Description | Include Steps, Expected, Actual in bullet form